## Sheet1
ID | Tower | Application Name | CI Name | No of Incident reduced per month | Expected SR count per month | Current Effort in Hrs per Month | Title | Assigned To | State | Tags | Work Item Type | Comment Mon 7/20 | TVL=Takeda Value Lead
2672 | Japan | SCRM-CRM | SCRM-BI | 20 | 0 | 30 | [Takeda Japan]Solve the incident of synchronous errors | kavana Jin Li <kavana.jin.li@accenture.com> | Scale - Test | Sprint 6; TVL | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2675 | Japan | SCRM-BI | SCRM-BI | 20 | 0 | 500 | [Takeda Japan]Change user's authority | kavana Jin Li <kavana.jin.li@accenture.com> | Scale - Build | Sprint 6; TVL | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2476 | Comm IT | SCRM-CRM |  | 10 | 0 | 0 | [Takeda Japan]Access rights for BI and DI | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2500 | Comm IT | SCRM-DI |  | 8 | 0 | 0 | [Takeda Japan]Resolve the disk space issue | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2847 | Comm IT | SCRM-CRM | SCRM-CRM | 1 | 1 | 1 | [Takeda Japan]System access stat reporting for SCRM-CRM(Month summary) | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2423 | Comm IT | SCRM-BI |  | 0 | 0 | 5 | [Takeda Japan]Market_MM Table | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2424 | Comm IT | SCRM-CRM |  | 0 | 0 | 2.5 | [Takeda Japan]CLM Used History Creation Manual | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2425 | Comm IT | SCRM-CRM |  | 0 | 0 | 2 | [Takeda Japan]MSL & PMS Report Regular Delivery | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2427 | Comm IT | SCRM-CRM |  | 0 | 0 | 1.5 | [Takeda Japan]Report Provide Task for BI Team | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2429 | Comm IT | SCRM-BI |  | 0 | 0 | 3 | [Takeda Japan]BI-SQL | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2430 | Comm IT | SCRM-BI |  | 0 | 0 | 3 | [Takeda Japan]Delivery Online | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2431 | Comm IT | SCRM-CRM |  | 0 | 0 | 2 | [Takeda Japan]Document Folder Maintenance | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2497 | Comm IT | SCRM-BI |  | 0 | 0 | 0 | [Takeda Japan]Performance Improvement-BI | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2498 | Comm IT | SCRM-DI |  | 0 | 0 | 0 | [Takeda Japan]Reduce Incidents | kavana Jin Li <kavana.jin.li@accenture.com> | Discover |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2499 | Comm IT | SCRM-DI |  | 0 | 0 | 0 | [Takeda Japan]Data Recovery | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2629 | Japan | SCRM-CRM | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Creat Check List For Change Request | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2630 | Japan | SCRM-CRM | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Create Manuals for Specific Task | kavana Jin Li <kavana.jin.li@accenture.com> | Discover |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2673 | Japan | SCRM-BI | SCRM-BI | 0 | 0 | 40 | [Takeda Japan]Monitor the operating status of the BI system | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2676 | Japan | SCRM-BI | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Improving Process | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2783 | Comm IT | SCRM-CRM | N/A | 0 | 0 | 5 | [Takeda Japan]Sending Of Tracking Data Materials | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create | 登录saleforce下载14个csv文件，作业分月初与月中，月初作业时，有一个登录天数访问0合计 ,月初作业没有，连接access数据库。数据处理之后将文件内容粘贴到excel对应的sheet页里，更改中央值，复制excel里的图片粘贴到ppt里，并更改ppt里的日期，最后带附件送信 | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
3015 | Comm IT | SCRM-CRM | SCRM-CRM | 0 | 0 | 2 | [Takeda Japan]Scrm landing status | kavana Jin Li <kavana.jin.li@accenture.com> | New | 登录saleforce下载三个csv文件，将文件内容粘贴到excel对应的sheet页里，更新数据表，更改执行表的用户同步和用户登录的数量，按下执行工作表的执行按钮，在新的Excel中，将结果表加工后的内容按配置文件显示 ，最后送信 | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
3028 | Comm IT | SCRM-CRM | CRM | 0 | 0 | 4 | [Takeda Japan]Salesforce Mail Log Getting | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2895 | [6 empty] | APMS-01689_【常庫品管理】キャンセル作業 |  |  | 连接oracle数据库，获取数据然后粘贴到excel里，点击script作成按钮生成bat文件，执行bat文件之后，再次查询数据然后将结果粘贴到excel里，最后送信
徐凯
陈爽
袁奇
鸿飞
| 2783 | [Takeda Japan]Sending Of Tracking Data Materials | 登录saleforce下载14个csv文件，作业分月初与月中，月初作业时，有一个登录天数访问0合计 , 月初作业没有，连接access数据库。数据处理之后将文件内容粘贴到excel对应的sheet页里， 更改中央值，复制excel里的图片粘贴到ppt里，并更改ppt里的日期，最后带附件送信 | 自动登录saleforce下载文件，自动连接数据库，自动进行数据处理，将处理后的数据写入到excel里，自动生成ppt，自动送信
| 2783 | [Takeda Japan]Scrm landing status | 登录saleforce下载三个csv文件，将文件内容粘贴到excel对应的sheet页里， 更新数据表，更改执行表的用户同步和用户登录的数量，按下执行工作表的执行按钮， 在新的Excel中，将结果表加工后的内容按配置文件显示 ，最后送信 | 自动登录saleforce下载文件。自动进行数据处理，将处理后的数据写入到excel里，更新数据表，更改登录数量，实现自动点击执行按钮，自动将结果表按配置文件显示，实现自动送信
| 2895 | APMS-01689_【常庫品管理】キャンセル作業 | 连接oracle数据库，获取数据然后粘贴到excel里，点击script作成按钮生成bat文件， 执行bat文件之后，再次查询数据然后将结果粘贴到excel里，最后送信 | 自动连接数据库获取数据，将结果写入到excel里，自动生成bat文件并执行，自动送信