## Sheet1
ID | Tower | Application Name | CI Name | No of Incident reduced per month | Expected SR count per month | Current Effort in Hrs per Month | Title | Assigned To | State | Tags | Work Item Type | Comment Mon 7/20 | TVL=Takeda Value Lead
2672 | Japan | SCRM-CRM | SCRM-BI | 20 | 0 | 30 | [Takeda Japan]Solve the incident of synchronous errors | kavana Jin Li <kavana.jin.li@accenture.com> | Scale - Test | Sprint 6; TVL | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2675 | Japan | SCRM-BI | SCRM-BI | 20 | 0 | 500 | [Takeda Japan]Change user's authority | kavana Jin Li <kavana.jin.li@accenture.com> | Scale - Build | Sprint 6; TVL | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2476 | Comm IT | SCRM-CRM |  | 10 | 0 | 0 | [Takeda Japan]Access rights for BI and DI | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2500 | Comm IT | SCRM-DI |  | 8 | 0 | 0 | [Takeda Japan]Resolve the disk space issue | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2847 | Comm IT | SCRM-CRM | SCRM-CRM | 1 | 1 | 1 | [Takeda Japan]System access stat reporting for SCRM-CRM(Month summary) | kavana Jin Li <kavana.jin.li@accenture.com> | New | 本次作业为月次作业 由于系统设计原因手动无法实现当前作业 只能通过自动化工具生成报表 发送给客户 工具具体实现功能 同过automation包从dataloader抽取300万条数据，通过openpyxl进行数据的分类处理，调用matplotlib汇总生成柱状图表，数据表，整合生成pdf | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2423 | Comm IT | SCRM-BI |  | 0 | 0 | 5 | [Takeda Japan]Market_MM Table | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2424 | Comm IT | SCRM-CRM |  | 0 | 0 | 2.5 | [Takeda Japan]CLM Used History Creation Manual | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2425 | Comm IT | SCRM-CRM |  | 0 | 0 | 2 | [Takeda Japan]MSL & PMS Report Regular Delivery | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2427 | Comm IT | SCRM-CRM |  | 0 | 0 | 1.5 | [Takeda Japan]Report Provide Task for BI Team | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2429 | Comm IT | SCRM-BI |  | 0 | 0 | 3 | [Takeda Japan]BI-SQL | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create | 担当者每周一早八点等待日本发来邮件 从邮件中下载存储数据的附件，按照日期处理抽出的数据分成多个数据源文件，将数据插入到数据库中，插入后进行验证，给日本发信 工具具体实现功能 通过调用微软win32com进行24小时自动监视邮件 自动获取邮件附件内容，通过openpyxl将数据按照日期进行分类， 通过cx_orca链接数据库 进行数据信息的插入，执行select操作进行插入信息的确认 并发信通知onshore | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2430 | Comm IT | SCRM-BI |  | 0 | 0 | 3 | [Takeda Japan]Delivery Online | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2431 | Comm IT | SCRM-CRM |  | 0 | 0 | 2 | [Takeda Japan]Document Folder Maintenance | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2497 | Comm IT | SCRM-BI |  | 0 | 0 | 0 | [Takeda Japan]Performance Improvement-BI | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2498 | Comm IT | SCRM-DI |  | 0 | 0 | 0 | [Takeda Japan]Reduce Incidents | kavana Jin Li <kavana.jin.li@accenture.com> | Discover |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2499 | Comm IT | SCRM-DI |  | 0 | 0 | 0 | [Takeda Japan]Data Recovery | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2629 | Japan | SCRM-CRM | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Creat Check List For Change Request | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2630 | Japan | SCRM-CRM | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Create Manuals for Specific Task | kavana Jin Li <kavana.jin.li@accenture.com> | Discover |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2673 | Japan | SCRM-BI | SCRM-BI | 0 | 0 | 40 | [Takeda Japan]Monitor the operating status of the BI system | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2676 | Japan | SCRM-BI | SCRM-BI | 0 | 0 | 0 | [Takeda Japan]Improving Process | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2783 | Comm IT | SCRM-CRM | N/A | 0 | 0 | 5 | [Takeda Japan]Sending Of Tracking Data Materials | kavana Jin Li <kavana.jin.li@accenture.com> | Co Create |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
3015 | Comm IT | SCRM-CRM | SCRM-CRM | 0 | 0 | 2 | [Takeda Japan]Scrm landing status | kavana Jin Li <kavana.jin.li@accenture.com> | New |  | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
3028 | Comm IT | SCRM-CRM | CRM | 0 | 0 | 4 | [Takeda Japan]Salesforce Mail Log Getting | kavana Jin Li <kavana.jin.li@accenture.com> | New | 担当着每月俩次按照日期从网页下载数据到本地 进行数据的处理(增删改) 将做好后的数据上传到sharepoint上 工具具体实现功能 用户手动启动工具，利用selenium实现网页操作，从网页下载数据到本地，通过xlwings进行数据的处理生成对应的文件，通过selenium进行文件的上传. | User Story | On Track; validate in separate meeting due to pending discussion w/ Vinod & Kavanna;
2894 | [9 empty] | 读取申请书内容 根据内容进行数据处理 从数据库读取数据 进行增删该查操作
2895
徐凯
陈爽
袁奇
鸿飞